## Report
Date | Task Name | Status | Person
2024-04-08 | Define Outlines | Complete | Adam
2024-04-08 | Data Format | Complete | Josh Poche
2024-04-17 | PA Report | Complete | Josh Poche
2024-04-17 | Parent Class | Complete | Adam
2024-04-17 | Child Class | In progress… | Adam, Josh Poche
2024-04-24 | PA Report | Complete | Josh Poche
2024-04-24 | Child Class | In progress… | Adam
2024-04-26 | Test Code in Main | In progress… | Adam
2024-04-26 | Fixes to Parent and Child Classes | In progress… | Adam
2024-04-26 | Config File | In progress… | Adam
2024-04-27 | Update Config File | In progress… | Adam
2024-04-27 | Update Child Class | In progress… | Adam
2024-04-28 | Child Class | Complete | Adam
2024-05-01 | Update Config File | Complete | Adam
2024-05-01 | Update Child Class | Complete | Adam
2024-05-01 | Test Code in Main | Complete | Adam
2024-05-01 | Fixes to Parent and Child Classes | Complete | Adam
2024-05-01 | PA Report | Complete | Josh Poche